## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a system, I want to automatically generate banking transactions so that transaction flow can be simulated. | Must | Problem statement approval | Blessy | Completed
Sprint 2 | Sprint 2 | US-02 | As a system, I want to store generated transactions in a database so that transaction history is maintained. | Must | Transaction generation module | Shital | Completed
Sprint 3 | Sprint 3 | US-03 | As a system, I want to validate transactions using predefined rules so that suspicious transactions can be identified. | Must | Stored transaction data | Nithya | Completed
Sprint 4 | Sprint 4 | US-04 | As a user, I want to detect fraudulent transactions using a machine learning model and view results through a user interface. | Must | Rule-validated transaction data | Blessy,Shital,Nithya | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7